## project
Feedback Control System Gantt Chart | [5 empty] | Period Highlight: |  |  |  |  | 14 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) |  |  |  |  | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | Date
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | 2013-09-29 | 2013-10-06 | 2013-10-13 | 2013-10-20 | 2013-10-27 | 2013-11-03 | 2013-11-10 | 2013-11-17 | 2013-11-24 | 2013-12-01 | 2013-12-08 | 2013-12-15 | 2013-12-22 | 2013-12-29 | 2014-01-05 | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02 | 2014-03-09 | 2014-03-16 | 2014-03-23 | 2014-03-30 | 2014-04-06 | 2014-04-13 | 2014-04-20 | 2014-04-27 | 2014-05-04 | 2014-05-11
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Meet with Lab Director to Discuss Project | 1 | 1 | 1 | 1 | 100%
Research the Topic to Understand Project | 2 | 2 | 3 | 2 | 100%
Meet with Lab Member to Discuss Questions | 3 | 1 | 4 | 1 | 100%
Brainstorm Ideas for Project | 3 | 2 | 3 | 2 | 100%
Discuss Ideas with Lab Director | 4 | 2 | 4 | 2 | 100%
Reiterate on Ideas and Decide on Implementation | 5 | 2 | 5 | 1 | 100%
Begin Implementation | 5 | 2 | 5 | 2 | 100%
Establish Pr. Sensor Comms | 6 | 2 | 6 | 3 | 100%
Pr. Regulator Control/comm | 6 | 1 | 6 | 5 | 0%
Gravity Cailbration Setup | 6 | 1 | 6 | 1 | 100%
Comm w 2xPerist., Syringe, Balance | 7 | 2 | 8 | 3 | 60%
1st Draft GUI | 8 | 2 | 9 | 2 | 25%
First 'Skeleton' System Test | 1 | 2 | 1 | 2 | 50%
Continue Hardware and Software Development | 11 | 4 |  |  | 0%
Discuss Potential Problems with Skeleton System | 15 | 2 |  |  | 0%
Finish Hardware, Continue Software | 16 | 3 |  |  | 0%
First Finished Prototype | 19 | 2 |  |  | 0%
Discuss Problems and Solutions | 20 | 2 |  |  | 0%
Test and Refine Prototype | 21 | 5 |  |  | 0%
Discuss Poster Presentation | 20 | 3 |  |  | 0%
Develop Poster and Demo for Poster Presentation | 22 | 8 |  |  | 0%
Second Finished Prototype | 26 | 2 |  |  | 0%
Discuss Problems and Solutions | 27 | 2 |  |  | 0%
Test and Refine Prototype | 27 | 3 |  |  | 0%
Final Implementation | 29 | 2 |  |  | 0%
Final Poster Session - Senior Design Day | 30 | 1 |  |  | 0%